## Sheet1
Week Number	Date	Stages	Progress Documented	Notes
Week 1	09/12/2024	Investigate	Database Found (10/12/2024), New one updated 17/12/24	Cleaning database started, Managed to remove rows I don't need as well, and update CSV too
Week 2	16/12/2024	Plan & Design
Week 3	06/01/2025	Plan & Design	(09/01/25)Cleaning Completed, removed any unwanted values/values I can't use in my visualisation. going to begin designing my Website today
Week 4	13/01/2025	Create
Week 5	20/01/2025	Create
Week 6	27/01/2025	Create
Week 7	24/02/2025	Evaluation
Week 8	03/03/2025	References
Week 9	10/03/2025	Submit